## ProjectSchedule
Radiation Tracking
Big Data |  | Project Start: | 2024-04-22
|  | Display Week: | 1 |  |  | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | Jun 17, 2024 | [6 empty] | Jun 24, 2024 | [6 empty] | Jun 31, 2024
[6 empty] | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-18 | 2024-05-19 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-25 | 2024-05-26 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Literature Review | Everyone | 80% | 2024-04-22 | 2024-04-27 | DAYS: 6
Stage 1:
Setting up Apache Kafka | Riya and Nikhil |  | 2024-04-29 | 2024-05-02 | DAYS: 4
Creating Kafka Producer | Radhika and Vivek |  | 2024-05-03 | 2024-05-14 | DAYS: 12
Providing dataset to Kafka | Riya and Radhika |  | 2024-05-15 | 2024-05-23 | DAYS: 9
Testing and Optimizing | Vivek and Nikhil |  | 2024-05-24 | 2024-05-29 | DAYS: 6
Stage 2:
Setting up Kafka Consumer | Radhika and Vivek |  | 2024-06-01 | 2024-06-08 | DAYS: 8
Create User Interface | Riya and Nikhil |  | 2024-06-09 | 2024-06-17 | DAYS: 9
Integrating Kafka and UI | Vivek and Nikhil |  | 2024-06-18 | 2024-06-25 | DAYS: 8
Testing for bugs | Riya and Radhika |  | 2024-06-26 | 2024-06-30 | DAYS: 5
Adding additional functionalities | Everyone |  | 2024-07-01 | 2024-07-06 | DAYS: 6
Final Presentation | Everyone |  | 2024-07-04 | 2024-07-06 | DAYS: 3
2018-01-13
Note on H5: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.